## Sheet1
| Week 2* | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Jasmine Ellis | > Rough draft of class diagram. > Research matching algorithms. > Learn how to use testing suite in lean testing. | > User story: sign up > Test case: valid login > Research: MongoDB | > User story: login > First draft of Project Charter > Initialise github > Research MongoDB | > Set up PostgreSQL database > User modelling > Function: user login > Function: user registration > Tests for: user model, user login > User story: Edit profile > Research: geocoder gem | > Function: edit profile > Users index page > Add geocoding to user model > Function: admin delete users > User stories: answer match questions, change match answers, profile image upload. > Document: 5 week schedule > Research: carrierwave gem | > Function: user image uploading > Add profile pic to user profile > Test: minimum age upon registration > Minimum age validation added to user registration function > Research: matching algorithms | > Profile model: add several user attributes to profile, remove said attributes from user table. Update application accordingly via controller and view. > Profile form (create, edit) > Add interests to profile > Add several "before_action" methods to controller relating to existence of profile for user, and non-existance of profile for admin. > Wireframe: user profile v. 2 | > Match modelling > Designed and implemented matching algorithm > Matches page > Add 'Hobbies' to interests | > Location and gender filtering applied 'create_match' method > Add 'Music' to interests > Function: search users on users index page > Bug fix: encoding compatibility error > Seed database with 200 test users > Add method to redirect homepage when logged in > Add method to update matches when user updates certain profile attributes. | > Deploy to Heroku and seed production database > Assist with liking function > Bug fix: google fonts not working in Heroku | > Check and compile minutes, user stories > Add additional tests to users and profiles controller test files > Tools setup guide > Ensured lean testing suite was up to date, added several test cases > Proof read all documentaiton
| Hours: 5 | Hours: 10 | Hours: 10 | Hours: 15 | Hours: 10 | Hours: 10 | Hours: 15 | Hours: 10 | Hours: 10 | Hours: 8 | Hours: 15
Haotian Xu | > Research matching algorithms. > Research Rails. | > Wireframes: Registration > Wireframes: Homepage > Wireframes: Login > Research: Rails, git, cloud9 with AWS | > Designed several logos > Frontend: homepage, login (done separate from app) >Research: Rails,Heroku, MVC | > Frontend: Homepage layout > Frontend: Login layout > Wireframe: Edit profile > Wireframe: User profile > Research: Rails | > Frontend: Registration > Add logo to layout > Wireframes: Match questions page > Wireframes: View other's match answers > Wireframes: View own match answers > Research: Rails, Algorithms | > Wireframe: matches page > UI: Modify logo size, login button > Frontend: Modify logo section( repalce image text by title) > Frontend: Mobile version optimization > Research: GEM Carrierwave, imageuploader & Ajex uploader | > Remove unused css and js files that came with template > Fixed rails bootstrap issue > Fixed: jQuery version issue > Debug: fix consoles erros > User gzip to compress content > Frontend: Edit profile form > Special consideration: Application number- SW1720446 | > Frontend: Logo text > Remove IE related code > Research: How to make it work on AWS > Research: How to send an email via SMTP > Special consideration: Application number- SW1720446 | >Frontend: add meta viewport for mobile >Frontend: Add new route -pages-, add controller and file > Research: How to recall git commit | >Frontend: Remove avatar on footer >Fronted: Help page >Frontend: Replace read more link on blog section > User story: Ensure all user stories are up to date > Research: How to add an domain | >Frontend: Replace dating advice by social media >Frontend: Terms&Conditions page >Frontend: Support page >Frontend: Privacy page >Frontend: FAQ page >Frontend: CSS colour conflict > Added a real domain http://matchmeplease.me Research: How to get a domain name and DNS configuration
| Hours: 5 | Hours:8 | Hours: 13 | Hours: 15 | Hours: 10 | Hours: 13 | Hours: 6 | Hours: 3 | Hours: 5 | Hours: 8 | Hours: 13
Xieyang Wu | > Research matching algorithms. > Research Rails. | > Research: Rails, MVC | > Test cases: login, registration. > Research: Rails, MVC | > Test cases: delete account, view profile, edit profile > Research: Rails | > Test cases: view match answers, answer match questions, view match answers (other user) > Integration test: admin delete other users > Research: Rails | > Integration tests: non-admin cannot delete user | > Tests: modify user tests to accommodate for updates to database > Test cases: image uploading (part of registration and edit profile), edit profile, edit account settings, browse matches | > Started model tests for profile. > Research: Rails | > Modify test case for view profile and edit profile | > Tests: profile model, user model, likeable model | >Test: User controller tests >Test case:Integration C9,Test case: models C9,Test case: Controllers C9 >Testing Register >Class diagram >Ensured lean testing suite was up to date
| Hours: 6 | Hours: 6 | Hours: 13 | Hours: 48 | Hours: 10 | Hours: 6 | Hours: 12 | Hours: 8 | Hours: 8 | Hours: 8 | Hours: 15
Hao Li | [Hao did not join our until Thursday of week 3] | > Research: AWS and Rails > Research: Git and Github | > User story: Logout > Research: Rails, MVC > Continued to work on deploying app to AWS | > Research: PostgreSQL, Rails > User story: view profile > User story: delete account | > User story: view match answers (own) > Function: delete own account > Research: AWS, EC2, Passenger, Nginx, Rails | > First deploy to Heroku | > UI: users index, profile > User stories: sign up (revision), edit profile (revision), edit account settings > Debug issues with JS in production | > Test case: view matches > UI modifications | > UI: improve profile form | > Function: Like/unlike other user > Likes page > Liked By page > UI: Improve layout for sign in and account settings | > Documentation:Databse schema > Documentation:Risk register > Test: Black box test the profermence of website which in Heroku server and fix bug > Documentation: User manual
| Hours: n/a | Hours: 6 | Hours: 13 | Hours: 8 | Hours:15 | Hours: 7 | Hours: 9 | Hours: 10 | Hours: 10 | Hours: 18 | Hours: 13
* We did not form our group until Wednesday of week 2.